## P5-08
Priority | Finding ID | Finding | CVSS | Severity | Recommendation | Effort Estimate | Business Rationale
1 | P3-02 | Agent Identity Spoofing | 8.1 | HIGH | Implement strong agent identity verification, signed service-to-service authentication, least-privilege permissions, and explicit authorization checks before sensitive actions. | 3–5 days | Reduces the chance that an attacker can impersonate an AI agent and perform privileged actions. This protects system integrity and limits unauthorized business operations.
2 | P3-04 | RAG Poisoning | 8.1 | HIGH | Strengthen RAG ingestion controls with trusted-source allowlists, document validation, provenance tracking, content scanning, and an approval process for high-risk knowledge sources. | 4–6 days | Reduces the risk of poisoned knowledge entering the AI system and influencing answers or downstream decisions. Protects decision quality and business trust.
3 | P3-04-MCP | MCP Tool Abuse After RAG Poisoning | 8.1 | HIGH | Add MCP/tool authorization gates, tool allowlists, scoped credentials, parameter validation, and human approval for high-impact tool calls originating from untrusted or retrieved content. | 4–7 days | Limits the blast radius if RAG content is compromised. Prevents malicious retrieved instructions from directly triggering sensitive business actions.
4 | P3-01 | Indirect Prompt Injection / Credential Exposure | 7.1 | HIGH | Add prompt-injection defenses, isolate secrets from model context, apply input/content filtering, and prevent credentials or sensitive tokens from being exposed to the model. | 3–5 days | Reduces the risk of prompt manipulation leading to credential exposure. Protects confidential information and lowers the likelihood of account or system compromise.
5 | P3-03 | System Prompt Extraction | 6.5 | MEDIUM | Protect system prompts and sensitive instructions using server-side controls, minimize sensitive information in prompts, and add output filtering and access controls for prompt-related data. | 2–4 days | Reduces information leakage about system instructions and security controls. Makes targeted prompt-based attacks harder while preserving normal AI functionality.